## Project Budget Sheet
Project Budget Sheet
Project Name: [Project Name] |  |  |  | Prepared by: xltemplates.org
Project Manager: [Project Manager's Name]
Start Date: [MM/DD/YYYY]
End Date: [MM/DD/YYYY]
Prepared By: [Preparer's Name]
Date Prepared: [MM/DD/YYYY]
Budget Summary
Budget Category | Budgeted Amount | Actual Amount | Variance | Notes
Labor Costs | 2000 | 1900 | 100 | [e.g., Overtime costs]
Materials & Supplies | 2500 | 2400 | 100 | [e.g., Price changes]
Equipment & Tools |  |  | 0 | [e.g., Rental vs Purchase]
Subcontractors |  |  | 0 | [e.g., External services]
Travel Expenses |  |  | 0 | [e.g., Airfare, Lodging]
Permits & Fees |  |  | 0 | [e.g., Government fees]
Contingency |  |  | 0 | [e.g., Unexpected costs]
Miscellaneous |  |  | 0 | [e.g., Other expenses]
Total | 4500 | 4300 | 200
Detailed Budget Breakdown
Labor Costs
Role/Position | Hourly Rate | Estimated Hours | Budgeted Amount | Actual Hours | Actual Amount | Notes
[e.g., Project Manager] | 50 | 25 | 1250 | 30 | 1500 | [e.g., Additional hours needed]
[e.g., Engineer] | 75 | 2 | 150 | 30 | 2250 | [e.g., Overtime]
[e.g., Laborer] |  |  | 0 |  | 0 | [e.g., Additional resources]
|  |  | 1400 |  | 3750
Materials & Supplies
Material/Supply | Unit Cost | Quantity | Budgeted Amount | Actual Quantity | Actual Amount | Notes
[e.g., Concrete] | 100 | 25 | 2500 | 30 | 3000 | [e.g., Price increase]
[e.g., Lumber] | 75 | 5 | 375 | 30 | 2250 | [e.g., Supplier change]
[e.g., Paint] |  |  | 0 |  | 0 | [e.g., Extra coats needed]
|  |  | 2875 |  | 5250
Equipment & Tools
Equipment/Tool | Rental/Purchase | Quantity | Budgeted Amount | Actual Quantity | Actual Amount | Notes
[e.g., Excavator] | 150 | 25 | 3750 | 30 | 4500 | [e.g., Extended rental period]
[e.g., Drill] | 90 | 5 | 450 | 30 | 2700 | [e.g., Replacement needed]
[e.g., Safety Gear] |  |  | 0 |  | 0 | [e.g., Extra supplies ordered]
|  |  | 4200 |  | 7200
Subcontractors
Subcontractor | Service Provided | Budgeted Amount | Actual Amount | Notes
[e.g., Electrical Contractor] | [Electrical Wiring] | 1500 | 1600 | [e.g., Scope change]
[e.g., Plumbing Contractor] | [Plumbing Installation] | 1200 | 1400 | [e.g., Extra repairs needed]
Additional Costs
Travel Expenses
Expense Category | Budgeted Amount | Actual Amount | Notes
[e.g., Airfare] | 100 | 150 | [e.g., Flight change fee]
[e.g., Hotel] | 250 | 254 | [e.g., Additional nights]
[e.g., Meals] | 365 | 250 | [e.g., Team meals]
Permits & Fees
Permit/Fee | Budgeted Amount | Actual Amount | Notes
[e.g., Building Permit] | 200 | 250 | [e.g., Expedited processing]
[e.g., Environmental Fee] |  |  | [e.g., Additional inspection]
Contingency & Miscellaneous
Expense Category | Budgeted Amount | Actual Amount | Notes
[e.g., Unforeseen Repairs] | 100 | 110 | [e.g., Structural issues]
[e.g., Miscellaneous Expenses] |  |  | [e.g., Office supplies]
Total Project Costs
Category | Budgeted Amount | Actual Amount | Variance
Labor Costs | 1400 | 3750 | 2350
Materials & Supplies | 2875 | 5250 | 2375
Equipment & Tools | 4200 | 7200 | 3000
Subcontractors | 2700 | 3000 | 300
Travel Expenses | 715 | 654 | 61
Permits & Fees | 200 | 250 | 50
Contingency & Miscellaneous | 100 | 110 | 10
Total Project Cost | 12190 | 20214 | 8024
Budget Review and Approval
Reviewed By: __________________________ |  |  | Date: [MM/DD/YYYY]
Approved By: __________________________ |  |  | Date: [MM/DD/YYYY]