## Renovation Budget Sheet
Home Renovation Budget Sheet
Category | Estimated Cost | Actual Cost | Difference | Comments
Design/Planning | 2654 | 2658 | 4 | [Architect fees, permits]
Demolition | 2145 | 2541 | 396 | [Tearing down walls, debris removal]
Foundation/Structural Work | 2312 | 2154 | 158 | [Reinforcement, foundation repair]
Framing | 1256 | 1254 | 2 | [Walls, partitions]
Electrical Work | 3695 | 3569 | 126 | [Wiring, outlets, fixtures]
Plumbing | 2541 | 2145 | 396 | [Pipes, sinks, water lines]
HVAC (Heating/Cooling) | 1254 | 1256 | 2 | [Air conditioning, heating systems]
Windows/Doors | 1256 | 1258 | 2 | [Window and door replacements]
Roofing | 1236 | 1326 | 90 | [Roof repairs or replacement]
Flooring | 1525 | 1252 | 273 | [Hardwood, tiles, carpets]
Painting | 1256 | 1562 | 306 | [Interior and exterior]
Cabinetry & Carpentry | 2542 | 2452 | 90 | [Kitchen cabinets, shelving]
Appliances | 1236 | 2361 | 1125 | [Stove, refrigerator, washer]
Fixtures | 1254 | 1258 | 4 | [Lighting, faucets]
Landscaping | 1254 | 5221 | 3967 | [Gardens, lawns, driveways]
Miscellaneous | 1256 | 2547 | 1291 | [Contingency, unforeseen expenses]
Total Estimated Cost | 28672
Total Actual Cost |  | 34814
Total Difference |  |  | 6142
Instructions:
1. Category: Break down the renovation into detailed categories.
2. Estimated Cost: Record the initial budget or quote for each category.
3. Actual Cost: Track the actual expenses incurred as the project progresses.
4. Difference: Calculate the variance between the estimated and actual costs.
5. Comments: Add notes for clarification, changes, or adjustments (e.g., delays, additional expenses).
Notes:
Regular Updates: Keep the budget sheet updated as the project advances.
Contingency: Include a contingency line item for unexpected costs (typically 10-20% of the total budget).
Review Costs: Periodically review the sheet to ensure the project stays on budget or adjust as necessary.