## Checklist
Construction Site Checklist
Today: | 2025-01-15 | Site Manager: | Mr. Miko Do
Site Address: | [Address Line 1] | Site Inspector: | Ms. Suzo Lue
[Address Line 2]
Checklist:
Task No. | Task Description | Assigned To | Deadline | Completion Status | Comments | Date Completed | Progress (%)
1 | Inspect site safety equipment | Safety Officer | 2025-01-15 | Pending |  |  | 0%
2 | Check structural foundations | Engineer Team A | 2025-01-20 | In Progress | Foundation cleared |  | 50%
3 | Secure perimeter fencing | Contractor XYZ | 2025-01-17 | Done | Completed on time | 2025-01-16 | 100%
4 | Set up temporary utilities | Electrical Team | 2025-01-18 | Pending | Delayed due to rain |  | 0%
[6 empty] | Overall Progress: | 37.5%