## Checklist
Project Completion Checklist
A Project Completion Checklist ensures that all necessary tasks are completed before closing a project. It includes company details, project milestones, and verification checks.
Company Information
ABC Construction Ltd. |  |  |  | Project Manager: | John Doe
123 Main Street, Springfield, XY 45678 |  |  |  | Project Name: | Downtown Commercial Complex
(123) 456-7890 |  |  |  | Project Start Date: | 2024-01-10
info@abcconstruction.com |  |  |  | Project End Date: | 2025-03-15
✅ Project Completion Tasks
Task No. | Task Description | Responsible Person | Start Date | End Date | Status | Remarks
1 | Final Site Inspection | Site Engineer | 2025-03-10 | 2025-03-12 | Pending | Awaiting approval
2 | Equipment & Material Return | Logistics Team | 2025-03-08 | 2025-03-10 | Completed | ✔️
3 | Final Client Walkthrough | Project Manager | 2025-03-12 | 2025-03-14 | InProgress | Scheduled for 12th
4 | Documentation Handover | Admin Team | 2025-03-10 | 2025-03-13 | Pending | Pending final sign-off
4 | Financial Settlement & Invoicing | Accounts Team | 2025-03-10 | 2025-03-15 | Pending | Processing payments
|  |  |  | Task Completion Percentage (%): |  | 20%
📌 Final Sign-Off Section
Authorized By |  | Position |  | Signature |  | Date
John Doe |  | Project Manager
Jane Smith |  | Quality Control
Client Name |  | Client Representative